## Sheet1
Defect ID | Feature/Use Case ID | Description | Steps To Reproduce | Test Case ID | Expected Result | Actual Result | Defect Severity | Defect Priority | Reporter | Assigned To | Status (Open/Closed) | Notes
D-01 | Checkout Feature | User is logged in, User tries to checkout an out of stock product | 1. User is logged in 2. User adds an out of stock product 3. User checks out the product |  | User can't buy out of stock products | User was able to buy out of stock products | High | High | Nick Chu |  | Open | API tests pass, but frontend sends a request with no body to backend resulting in this defect
T2P3-86 | Create/Update Product | Products can be created without essential information | 1. Admin is logged in 2. Admin creates a new product 3. Admin doesn't enter any information | T2P3-81 | Admin can't create products with no information/description | Product is successfully created | Low | Low | Griffin Chambers |  | Open | Fields marked as required are not listed as such in HTML
T2P3-87 | Create/Update Product | Products can be updated with all essential information removed | 1. Admin is logged in 2. Admin removes information on a product 3. Admin updates a product's information | T2P3-79 | Admin can't update the product's information after removing all the information | Product is updated and becomes blank | Low | Low | Griffin Chambers |  | Open | Fields marked as required are not listed as such in HTML
T2P3-88 | Create/Update Product | When editing a product the price input is appended with a ".00" regardless if the input already has a decimal | 1. Admin is logged in 2. Admin views product on "Edit Products" page | T2P3-78 | The price of a product should be displayed as for example "19.00" | The price is displayed as "19.00.00" | Low | Low | Griffin Chambers |  | Open
MTD-900 | Register | The use can create accounts with invalid passwords. | 1. Type any first and last name into the input fields. 2. Type an invalid password into the password field. | MT-900 | The user cannot create an account with an invalid password. | The user creates an account with an invalid password | High | Low | Jody Roane |  | Open | This defect was found using a manual test.
MTD-901 | User Profile | The use can change account password to an invalid password. | 1. Type any first and last name into the input fields. 2. Type an invalid password into the password field. | MT-901 | The user cannot update an account with an invalid password. | The user updates an account with an invalid password | High | Low | Jody Roane |  | Open | This defect was found using a manual test.