## Defect Report
Defect ID | Feature/Use Case ID | Description | Steps To Reproduce | Test Case ID | Expected Result | Actual Result | Defect Severity | Defect Priority | Reporter | Assigned To | Status (Open/Closed) | Notes
D-01 | Checkout Feature | User is logged in, User tries to checkout an out of stock product | 1. User is logged in 2. User adds an out of stock product 3. User checks out the product | T2P3 - 71 | User can't buy out of stock products | User was able to buy out of stock products | 5 | 5 | NicK Chu | Nick Chu | Open
D-02 | Create/Update Product | Products can be created without essential information | 1. Admin is logged in 2. Admin creates a new product 3. Admin doesn't enter any information |  | Admin can't create products with no information/description | Product is successfully created | 2 | 2 | Griffin Chambers | Griffin Chambers | Open
D-03 | Create/Update Product | Products can be updated with all essential information removed | 1. Admin is logged in 2. Admin removes information on a product 3. Admin updates a product's information |  | Admin can't update the product's information after removing all the information | Product is successfully updated | 2 | 2 | Griffin Chambers | Griffin Chambers | Open
D-04 | Create/Update Product | When editing a product the price input is appended with a ".00" regardless if the input already has a decimal |  |  | The price of a product should be displayed as for example "19.00" | The price is displayed as "19.00.00" | 2 | 1 | Griffin Chambers | Griffin Chambers | Open
MTD-900 | Register | The use can create accounts with invalid passwords. | 1. Type any first and last name into the input fields. 2. Type an invalid password into the password field. | MT-900 | The user cannot create an account with an invalid password. | The user creates an account with an invalid password | High | Low | Jody Roane |  | Open | This defect was found using a manual test.
MTD-901 | User Profile | The use can change account password to an invalid password. | 1. Type any first and last name into the input fields. 2. Type an invalid password into the password field. | MT-901 | The user cannot update an account with an invalid password. | The user updates an account with an invalid password | High | Low | Jody Roane |  | Open | This defect was found using a manual test.

## RTM
Requirement ID | Requirement Description | Testcase ID | Testcase Description | Test Designer | Status | Defects | Defect ID | Defect Status
T2P3-116 | As a User or Admin, I should be able to log into the application | T2P3-26 | Manual Test, Postive Test, Negative Test, End Point Test. | Jody Roane | Passed
T2P3-115 | As a User, I should be able to register a new account | T2P3-22, MT-900 | Manual Test, Postive Test, Negative Test, End Point Test. | Jody Roane | Failed | The user can register a new account with an invalid password. | MTD-900 | Open
T2P3-105 | As a User Guest or Admin, I should be able to see a list of available products for me to add to my cart | T2P3 - 65 | The user can see all displayed products | Nick Chu | Passed
T2P3-102 | As a User or Guest, I should be able to checkout with the items in my cart, purchasing them and removing them from the inventory | T2P3 - 70 | The user checks out items in their cart | Nick Chu | Passed
|  | T2P3 - 71 | The user can't checkout an empty cart | Nick Chu | Passed
|  | T2P3 - 71 | The user can't buy an out of stock product | Nick Chu | Failed | User can checkout a product that is out of stock | D-01 | Open
T2P3-104 | As a User or Guest, I should be able to add items to my cart that I will later purchase or remove from my cart | T2P3 - 72 | The user adds products to cart | Nick Chu | Passed
T2P3-99 | As a User Guest or Admin, I should be able to change the color scheme from the normal mode to a dark mode option | T2P3 - 129 | The user can turn on dark mode | Benjamin Mizell | Passed
T2P3-100 | As a User Guest or Admin, I should be able to search the product list to better find the item(s) I am interested in | T2P3 - 130 | The user can search for specific products | Benjamin Mizell | Passed
T2P3-114 | As a User, I should be able to create and maintain a profile page | T2P3-2, MT-901 | Manual Test, Postive Test, Negative Test, End Point Test. | Jody Roane | Failed | The user can update their account with an invalid password. | MTD-901 | Open
T2P3-100 | As a [User¦Admin¦Guest¦Employee], I should be able to remove items from my cart within the Cart View | T2P3 - 131 | The user can add product quantity | Benjamin Mizell | Passed
|  | T2P3 - 132 | The user can remove product quantity | Benjamin Mizell | Passed
|  | T2P3 - 133 | The user can change product quantity | Benjamin Mizell | Passed
T2P3-101 | As a User, I should be able to view a list of all my previous orders and access the details of each order | T2P3 - 134 | The user can view their past orders | Benjamin Mizell | Passed
T2P3-17 | As a User or Admin, I should be able to reset my password | Password Reset | The user can reset their password | Griffin Chambers | Untested | SMTP Server not setup
T2P3-77 | As an Admin, I should be able to create new products and update existing products | Admin Creates Product | Admin should be able to create new products | Griffin Chambers | Passed
|  | Admin Updates Product Information | Admin should be able to update product information | Griffin Chambers | Passed | Displayed price is incorrect on Edit page only | T2P3-88 | Open
|  | Update Product Negative | Admin shouldn't be able to remove necessary product information | Griffin Chambers | Failed | All essential information can be removed without deleting product | T2P3-87 | Open
|  | Delete Product | Admin should be able to delete products | Griffin Chambers | Passed
|  | Create Product Negative | Admin shouldn't be able to create products missing required information | Griffin Chambers | Failed | Null products can be added to database | T2P3-86 | Open
T2P3-7 | As a User, I should receive notifications when a transaction has occurred | Notification of Successful Transaction | The user recieves a notification for order success | Griffin Chambers | Untested | SMTP Server not setup
T2P3-45 | As a User, Guest or Admin, I should be able to search the product list to better find the item(s) I am interested in | T2P3-92 | User searches using exact product name | Andrew Heckel | Passed
|  | T2P3-93 | user searches using a substring contained by multiple products | Andrew Heckel | Passed
|  | T2P3-94 | user searches using a string not contained by any product names | Andrew Heckel | Passed
T2P3-125 | As a logged in user, I should be able to rate and comment a product and have that review be visible in the product description. | T2P3-95 | A user is logged in and adds a review to a product | Andrew Heckel | Untested
|  | T2P3-96 | A user is not logged in and attempts to place a review on a product | Andrew Heckel | Untested
|  | T2P3-100 | A logged in user removes a review they made | Andrew Heckel | Untested
|  | T2P3-126 | Manual test of adding a review | Andrew Heckel | Passed
|  | T2P3-127 | A manual test of attempting to leave a review on a product while not logged in | Andrew Heckel | Passed
|  | T2P3-128 | A manual test of removing a review left by the user | Andrew Heckel | Passed
T2P3-64 | As any user I should be able to view the details of a product. | T2P3